## Environmental Impact Statement
Project Coordination Point | HQ Task | Task Responsibility | Meeting Topics | Deliverable to HQ | Attendees | HQ Review Periods - Working days
OSMRE Decision to Prepare EIS | Review and Maintain CEQ-OEPC Tracking Files | Region | N/A | Evaluation of Proposed action for NEPA Compliance Form (NEPA Form) | N/A | 2 days
OSMRE Internal “Kick-off” Meeting | Review and provide Department updates | Region | Senstive Issues Data Colllection Status Agency Coordination Requests; Scoping/Public Satus Review NOI and Schedule | Meeting Agenda Draft Schedule List of data available | Regional Team Solicitors HQ Staff | Meeting held within 30-days after NEPA Form to HQ
1. DEPARTMENT - Inital Action Notice | Review | Region | No Review Team Meeting Required | DEPARTMENT Review Team materials | N/A | 5 days
OSMRE Project Work Plan and Final Schedule | Review | Region | Project Approach, Public and Agency Involvement, data status | public and agency coordination stradegy, MOUs and Final Project Schedule | Region Team, HQ Staff, Solicitors, and Office of Communications (OC) | 3 days
2. DEPARTMENT Notice of Intent | Review and Coordination | Region | No Review Team Meeting Required | DEPARTMENT Review Team materials | N/A | 5 days
OSMRE EIS Development | Review | Region | EIS Outline, Data, Draft Analysis Methodologies, and schedule status | Agenda Annotated Outline | Regional Team Solicitors HQ Staff | 1 week
EIS Check-in | Director Briefing Coordination | HQ and Region | EIS Status and potential red flags | Briefing memo, Department Review Team Materials and Updated Schedule | Deputy Dir. HQ Staff, Region PM Solicitors | 5 days
OSMRE Internal Review DEIS - Chapters 1-2 | Review | Region and HQ | Status Update – Technical Analyses; Agency Coordination; Impacts; Public and Agency Involvement; Schedule | Meeting Agenda | Regional Team; Solicitors; HQ Staff | N/A
3. DEPARTMENT DEIS Development Briefing | Review and Coordination | Region | DEPARTMENT Review - project approach and plan for development of the EIS | DEPARTMENT Review Team materials | Review Team | 2 weeks
Internal Review EIS Chapters 3-5 | Review | Region | N/A | Draft Chapters 3-5 Schedule Update | N/A | 1 week
DEIS NOA Review | Review Draft NOA | Region and HQ | N/A | DEIS, Draft NOA and schedule for FR Notice | N/A | 2 days
Solicitor Review | -- | Regional Solicitor (HQ as needed) | N/A | Draft EIS | N/A | 2 weeks
Director Briefing | Director Briefing Coordination | HQ | DEIS Findings and Review Team Presentation | Draft Department Review Team presentation and review materials | Deputy Dir. HQ Staff; OC Region Dir Region Team solicitor | 1 week
4. DEPARTMENT Draft EIS and NOA Clearance | Review and Coordination | Region | DEPARTMENT Review Team Submittal | DEPARTMENT Review Team materials | Review Team | 2 weeks
Responses to DEIS Comments | Review | Region - Conference Call | Public Comments Draft Responses, and Schedule Update | Agenda; Draft response Schedule Update | Region PM; Solicitors and HQ Staff HQ Solicitor | 1 week
Internal FEIS Review | Review FEIS | Region and HQ |  | Draft FEIS | N/A | 2 weeks
Solicitor Review | --- | Regional Solicitor | N/A | Draft Final EIS | N/A | 2 weeks
Director Briefing | Director Briefing Coordination | HQ and Region | FEIS Findings and Review Team Presentation | Draft Department Review Team presentation and review materials | Deputy Dir. HQ Staff; OC Region Dir Region Team solicitor | 1 week
5. DEPARTMENT Final EIS and NOA Clearance | Review and Coordination | Region | EIS Update and NEPA Review Status | Final EIS-Draft ROD prior to Public Release | Review Team | 2 weeks
Internal ROD and NOA Review | Review ROD | Region and HQ | N/A | Draft Rod and FEIS Comments | N/A | 2 weeks
Solicitor Review | --- | Regional Solicitor | N/A | Draft- Final EIS | N/A | 2 weeks
Director Briefing | Director Briefing Coordination | HQ and Region | FEIS Finding and ROD | final ROD | Director, HQ Staff, Region Dir., Region Team, Solicitor, and OC | 1 week
6. DEPARTMENT ROD and NOA Clearance | Review and Coordination | Region | EIS Update and NEPA Review Status | Final EIS-Draft ROD prior to Public Release | No Review Team Meeting Required | 2 weeks
OSMRE GUIDE - NEPA Review and Coordination Points
Environmental Impact Statements (EIS)